## Schedule
Project schedule with Gantt chart
Project | Kardex rollout | Owner | Laura | Schedule start | 2026-03-02
Project schedule with Gantt chart
No. | Task | Owner | Start | Finish | Duration (days) | % complete | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12
1 | Inventory assessment | Laura | 2026-03-02 | 2026-03-06 |  | 100%
2 | Warehouses and locations | Laura | 2026-03-05 | 2026-03-11 |  | 100%
3 | Loading products into the system | Andres | 2026-03-09 | 2026-03-20 |  | 80%
4 | Initial physical count | Marta | 2026-03-18 | 2026-03-25 |  | 40%
5 | Team training | Andres | 2026-03-23 | 2026-03-27 |  | 0%
6 | Go live | Laura | 2026-03-30 | 2026-04-03 |  | 0%
Total project duration

## Instructions
Instructions
What it is
A project schedule with its Gantt chart: every task with dates, duration and
progress, plus one bar per week that paints itself.
How to use it
1. Enter the project, the owner and the schedule start date.
2. One row per task with its start and finish; duration is calculated.
3. The completion percentage is your figure: 0 is not started, 1 is finished.
4. The twelve columns on the right are weeks: the grey bar appears in the weeks the task
covers, with no painting by hand.
How to read it
A task starting on 9 March and finishing on 20 occupies the weeks between
those dates, not all twelve. Overlapping bars are tasks running in parallel: that is where
owners collide and where projects usually slip.
Worked example
Six tasks between 2 March and 3 April: assessment, warehouses, product
loading, physical count, training and go live. Product loading and the count overlap on
purpose.
Mistakes to avoid
· Setting the finish before the start: duration comes out negative.
· Changing the schedule start date without reviewing the tasks: the bars move, the typed
dates do not.
· Entering progress as a whole number (80) in a percentage cell: type 0.8 instead.
Notice
Internal control tool. It is not an official tax or accounting document: amounts and percentages are editable and the template calculates no taxes.
Kardex Tauro template · kardex-tauro.muisca.co